PIG SNP CHIP – April 18th Meeting/Conference Call

ATTENDEES

EUROPE

Alan Archibald – Roslin Institute

Christian Bendixen – Danish Institute of Agricultural Science

Richard Crooijmans – Wageningen University

Martien Groenen – Wageningen University

Miguel Perez-Enciso – Universitat Autonoma de Barcelona

Fahim Amini – Illumina, Nordic, UK & Ireland

Lene Berlick – Illumina, Nordic & Baltic Countries

Ole Menssing – Illumina, North East Germany, Czech Republic, Poland

Armin Winands – Illumina, Europe

AMERICAS

Deb Hamernik – USDA-CSREES

Dan Nonneman – USDA/ARS U.S. Meat Animal Research Center

Gary Rohrer – USDA/ARS U.S. Meat Animal Research Center

Max Rothschild – Iowa State University

Bob Schnabel – University of Missouri Animal Science

Larry Schook – University of Illinois

Tim Smith – USDA/ARS U.S. Meat Animal Research Center

Max Rothschild – Iowa State University

Bob Schnabel – University of Missouri Animal Science

Jerry Taylor – University of Missouri Animal Science

Curt Van Tassell – USDA/ARS

Debora Bailey – Illumina

Dawn Barry – Illumina

Cindy Lawley – Illumina

Marylinn Munson – Illumina

Mark Van Oene – Illumina

ACTION ITEMS

- Marylinn Munson to send meeting notes to Deb Hamernik. Deb to provide edits/additions and send to Larry. Larry to review and send out to consortia

- Marylinn Munson to provide Illumina Tech Note on process for SNP’s being placed onto a iSelect Infinium BeadChip

- Jerry Taylor to create first draft on a flow diagram to circulate draft and get everyone’s agreement. Need to have final version for the whole project including

  - Sequencing/SNP discovery

  - Bioinformatic steps

  - SNP validation/selection

  - Placing SNPs into public repository

  - Timelines using 22nd August 2008 as an endpoint and working backwards

    - Finalized SNP list and all PO’s are provided by 5:00 pm Pacific Time 22nd August, 2008

- Need an agreed consistent approach for criteria and validation of

  - all SNPs generated by sequencing

  - all SNPs provided by third parties

- Alan Archibald (?) to confirm Andrea’s (sp?  Roslin Institute?) help with spacing/bioinformatics

- Alan Archibald (?) to confirm Mario Caccamo help with guidelines on getting SNPs into general public repository

- Curt Van Tassell to provide to Christian Bendixen information from Christian Haudenschild for doing analysis on Linux (takes only a couple minutes to run.)

DISCUSSIONS

- Review progress to date.

Construction of the Reduced Representation Libraries (RRL), Richard Crooijmans, Martien Groenen

There are 4 enzymes being used; HaeIII, MspI, AluI, and DraI. There are 5 libraries for each enzyme.  30 animals/pool.  The breeds include 4 commercial (Large White, Landrace, Duroc, Pietrain) and 1 non-commercial (wild boar);  Pools with all breeds are being sent to Christian Bendixen.  Pools with all breeds but wild boar are being sent to Tim Smith.

1.  HaeIII 2-3% of genome covered – libraries are made and sent to Bendixen for sequencing

2.  MspI – libraries are made

3.  AluI – libraries will be ready possibly beginning of May. ~50% more DNA with this enzyme.

4.  DraI - Just started (low DNA yields thus far)

Solexa Sequencing: Christian Bendixen/Genome Analyzer

Read lengths at 35 bp, 30x coverage final (6x/breed x 5 breeds).

- HaeIII

They have received 5 libraries for HaeIII.  Ran 1 at 4M reads/library.  Currently checking that seq is ok.  Expect to be done in 2-3 weeks.  Have not checked the redundancy of the libraries.

- MspI

Once they have finished sequencing HaeIII libraries, they will begin sequencing MspI libraries

3.  AluI

They estimate sequencing possibly beginning of May.

4.  DraI—not started yet

Estimate sequencing all done by the first week of June.

Curt Van Tassell will be sharing information from Christian Haudenschild for doing work on Linux taking only a couple minutes to run.

454 Sequencing:  Tim Smith & Dan Nonneman

150-200 bp/fragment at standard run.  11 runs, 12.5x depth, 114K SNPs spread over 47K contigs in a pool of 26 animals (Duroc, Landrace, Large White, Berkshire, Hampshire).  3x for the flanking sequence.

- HaeIII – libraries made and will start to sequence next week

- MspI – libraries made and will start to sequence next week

3.  Alu I – need another kit from Schook to sequence

4.  DraI – no plans to date

Organizing Bioinformatics: Curt Van Tassell and Jerry Taylor

Ralph Wiedmann is doing alignment.

Cattle group did the following

- resequencing MALDI assay for each SNP source type.

- Also should refer to nature genetics paper.  Link is http://www.nature.com/nmeth/journal/v5/n3/abs/nmeth.1185.html;jsessionid=46AC6B4B0C125CD569FADCB995B81CD9

Recommend placing a more stringent criteria for SNP discovery the further you go out in the Solexa sequence. Cindy Taylor recommended using 29 or 30 bp on genome analyzer for the point to adjust criteria (i.e., make criteria for SNP discovery more stringent at bp 29 or 30 of Solexa reads).

Have allele frequency.

Andrea (sp?  Roslin Institute?) – would it be possible for Andrea to contribute/help with spacing/bioinformatics?

Mario Caccamo (Ensembl) – would it be possible to enlist Mario help with how to get SNPs into general public repository? Archibald and Schook will follow up.

Want to place into public repository – sequence, MAF (by breed?), and genome coordinates.  Provide genome coordinates that are known, approximate for areas not as well known.

SNP Validation/Selection Team: Tim Smith, Jerry Taylor and Larry Schook

Half million SNPs will be sufficient to get minimal desired spacing.  Would prefer/target 1M SNPs.

How many fragments will be in 454 reads?

Use blunt end pairs.

Cattle group did the following

- Ignored any SNPs that occurred more than once at the end of the sequence to avoid repetitive elements.

- Resequenced the single pass Sanger reads from the Baylor assembly and did a substantial amount of filtering to obtain SNPs with a conversion rate of at least 80%. Most SNPs on the bovine SNP50 chip had a conversion rate of >95%.

Van Tassell will share his spacing algorithm with the pig group. His spacing algorithm should work with 35 bp reads.

The pig genome sequence is being generated by a BAC by BAC strategy so SNP spacing won’t be as problematic for pigs as it was with cattle (whole genome shotgun strategy).

Dan Nonneman is checking validation rate by creating Sequenom multiplex.

Martien/Christian are comparing two methods, checking on smaller samples.

Need an agreed consistent approach for validation of all SNPs between Europe and Americas before genotyping begins.

3) SNPs discovered to SNPs on chips

What is needed?

Steps involved (double click on picture below to get full document)

4) Finalize announcements and ordering timeline.

22nd August 2008 as an endpoint and working backwards, here is a suggested overall schedule

1st May 2008

– All RRL libraries are received by sequencing sites (Tim Smith and Christian Bendixen)

1st June 2008

– All Sequencing/SNP discovery done

1st July 2008

– All SNP validation is done

1st Aug 2008

– All Bioinformatics is done

22nd Aug 2008 5:00 pm Pacific

      - Finalize SNP list is received by Illumina.

      - All qualified PO’s are received by Illumina

      - All legal documents are finalized, signed, and received by Illumina

      - All SNPs are placed into public repository

      - All samples used to validate the array are provided to Illumina

22nd Aug 2008 5:00 pm